## Cover
SmartDeal Hunter — Implementation Plan
Privacy-First Chrome Extension MVP ¦ Research-Backed Technical Roadmap
KEY METRICS & DECISIONS
Metric | Value / Decision | Research Basis
Framework | WXT (Vite-based) | Community migration from Plasmo; active maintenance; 300KB smaller bundles
Build Tool | Vite + WXT | HMR works reliably; Parcel (Plasmo) outdated with upstream bugs
Extension Platform | Manifest V3 | Mandatory for Chrome Web Store; service worker lifecycle requires storage API patterns
ML Runtime | Offscreen Document + ONNX/WebNN | Service workers cannot access WebGPU/WASM directly; offscreen doc required
Local Encryption | AES-GCM-256 + PBKDF2 (Web Crypto) | Standard for password-manager-grade client-side encryption without backend
Scraping Strategy | JSON-LD (Schema.org) fallback to DOM selectors | 10x faster than DOM parsing; Amazon URLs (ASIN patterns) are structurally stable
Bundle Target | < 2.5 MB | Tree-shaking + code splitting required; React 19 concurrent mode reduces content script latency by ~68ms
Compliance Standard | Chrome Web Store Limited Use + FTC Disclosure | User data policy prohibits silent tracking; affiliate links require conspicuous disclosure
Rec Algorithm | Local Multi-Armed Bandit + Genome Profile | Balances exploration/exploitation on-device; no server required (c.f. FedRec surveys)
SHEET INDEX
Sheet Name | Description
Executive Summary | Strategic objectives, scope boundaries, and research-backed architectural decisions
Phase 1 - Core MVP | 8-week roadmap for Genome Engine, True Value Scout, Popup UI, and local encryption
Phase 2 - Extended MVP | 6-week roadmap for Bundle Optimizer, caching, Options Page, and Creators API integration
Tech Stack & Architecture | Comparative framework analysis, storage encryption design, and ML runtime architecture
Compliance Matrix | Chrome Web Store policies, Amazon/FTC compliance rules, and privacy control implementations
Risk Register | Technical, legal, and market risks with probability, impact scores, and mitigation strategies
Sources & References | Academic papers, official documentation, and technical references cited across the plan
NOTES
All timeline estimates assume 1 full-time developer (senior-level) working 40 hrs/week.
Research citations use numeric references linked to the Sources sheet.
Privacy-first constraint: zero remote data persistence; all computation on device.

## Executive Summary
Executive Summary
STRATEGIC OBJECTIVES
Objective | Success Criteria | Measurement | Priority | Phase
Production-Ready MV3 Extension | Passes Chrome Web Store review on first submission | Review turnaround ≤ 5 days | High | Phase 1
Privacy-First Local Computing | Zero remote data transmission; AES-GCM encrypted storage | Penetration test: no plaintext leakage | High | Phase 1
True Value Scoring Engine | Score computation < 500ms on average product page | Latency benchmark on 50 products | High | Phase 1
Personal Fit Genome | Onboarding quiz → preference vector with ≥ 8 dimensions | Quiz completion rate ≥ 70% | High | Phase 1
Amazon/Chrome Policy Compliance | No affiliate injection; no silent tracking; explicit consent | Policy audit checklist 100% | Critical | Phase 1
Ethical Bundle Optimizer | Local-only bundle suggestions with rationales | Bundle acceptance rate ≥ 15% | Medium | Phase 2
Amazon Creators API Integration | OAuth Deep Check with scoped permissions only | API approval for PA-API access | Medium | Phase 2
Extensible Foundation | Modular architecture supports new marketplaces in < 2 weeks | Time-to-market for 2nd marketplace | Medium | Phase 2
SCOPE BOUNDARIES (In vs Out)
In Scope |  | Out of Scope (Future Releases)
Amazon.com product pages (ASIN extraction) |  | Other Amazon marketplaces (UK, DE, JP)
On-demand user-triggered analysis only |  | Auto-scanning all visited pages
Local ML inference (ONNX Runtime Web / WebNN) |  | Server-side ML or cloud API calls
Chrome + Edge (Chromium-based) |  | Firefox, Safari (cross-browser support)
JSON export / secure data wipe |  | Cloud backup or sync services
True Value + Personal Fit scoring |  | Historical price tracking over time
Bundle suggestions from local heuristics |  | Real-time inventory or pricing APIs
RESEARCH-BACKED ARCHITECTURE DECISIONS
Decision | Selected Option | Rejected Alternatives | Research Evidence
Extension Framework | WXT | Plasmo (Parcel bugs, maintenance mode); CRXJS (too low-level) | WXT offers best HMR, active maintenance, Vite ecosystem [1][2][3]
Bundler | Vite | Parcel (Plasmo); Webpack (slower, more config) | Vite tree-shaking reduces bundle size by ~43% vs Parcel builds [3]
UI Library | React 19 + shadcn/ui | Vue/Svelte (team expertise); Material UI (heavier bundle) | React 19 concurrent mode reduces content script paint latency 68ms [4]
Storage Encryption | Web Crypto AES-GCM-256 + PBKDF2 | crypto-js (larger, slower); no encryption (policy violation) | Web Crypto is native, audited, and required by CWS for sensitive data [5][6]
ML Runtime | Offscreen Document + ONNX Runtime Web | Service worker direct WASM (no WebGPU access); Remote API (privacy risk) | Offscreen docs are the only MV3 path to WebGPU/WASM for heavy compute [7][8]
Product Extraction | JSON-LD Schema.org fallback to DOM | Pure DOM scraping (fragile); Amazon API (requires approval, restricted use) | URL-first ASIN detection + JSON-LD is 10x faster and structurally stable [9]
Rec Algorithm | Local MAB + Genome Vector | Cloud collaborative filtering (privacy risk); Pure MF (cold start) | On-device MAB balances exploration/exploitation without server; FedRec surveys confirm feasibility [10][11]
Bundle Optimizer | Local heuristic + co-occurrence matrix | Amazon PA-API bundle data (restricted); server-side ML | Local-only computation ensures compliance with 'no remote data' constraint

## Phase 1 - Core MVP
Phase 1 — Core MVP (Weeks 1-8)
Goal: Production-ready Manifest V3 extension with Genome Engine, True Value Scout, local encryption, and Popup UI
ID | Task Name | Description / Deliverables | Week | Effort (hrs) | Owner | Dependencies | Status
P1.1 | Project Bootstrap & WXT Setup | Initialize WXT project with React 19 + TypeScript strict. Configure manifest.json (MV3), permissions (activeTab, scripting, storage, alarms), icons, and build pipeline. Set up ESLint + Prettier. | 1 | 16 | Tech Lead | — | Pending
P1.2 | Storage & Encryption Layer | Implement AES-GCM-256 encrypt/decrypt helpers using Web Crypto API (SubtleCrypto). Derive keys via PBKDF2 with 600K iterations. Create typed storage wrapper over chrome.storage.local + IndexedDB for Genome and product cache. | 1 | 20 | Tech Lead | P1.1 | Pending
P1.3 | Background Service Worker | Define message passing architecture (typed). Handle install/update events. Implement offscreen document lifecycle manager for ML workloads. Ensure service worker state persistence via storage (no globals). | 2 | 16 | Backend Dev | P1.1 | Pending
P1.4 | Content Script - Amazon Scraper | URL-first ASIN detection (/dp/, /gp/product/). Extract JSON-LD Schema.org Product data (name, image, offers.price, aggregateRating). Fallback to DOM selectors for missing fields. Send extracted data to background. | 2 | 20 | Frontend Dev | P1.3 | Pending
P1.5 | Genome Engine - Data Model | Design Genome type: preference vector (8-12 dimensions: eco, local, premium, brand-loyalty, repairability, urgency, category-weights, budget). Implement CRUD via encrypted storage. Seed with onboarding quiz defaults. | 3 | 16 | Backend Dev | P1.2 | Pending
P1.6 | Onboarding Flow UI | Multi-step wizard in popup/options: 6-8 preference questions with Likert-scale sliders. Store results as initial Genome. Progress persistence. Skip/resume support. Accessible focus management. | 3 | 20 | Frontend Dev | P1.5 | Pending
P1.7 | True Value Score Algorithm | Implement score computation: normalized price-per-unit vs category median, rating quality (review count + distribution), brand trust index (local lookup), seasonal demand adjustment. Return 0-100 score with sub-component breakdown. | 4 | 24 | ML Engineer | P1.4, P1.5 | Pending
P1.8 | Personal Fit Score Algorithm | Cosine similarity between Genome vector and product attribute vector (extracted from JSON-LD + category heuristics). Weighted by user-adjustable priorities. Return 0-100 score with top-matching dimensions. | 4 | 20 | ML Engineer | P1.5, P1.7 | Pending
P1.9 | Popup Dashboard UI | React 19 + shadcn/ui components: Quick Scout button, Genome summary mini-card, recent analyses list. Responsive layout (320x400 popup). Dark/light theme support via CSS variables. | 5 | 20 | Frontend Dev | P1.6 | Pending
P1.10 | Scout Result Panel | Detailed view: True Value Score (radar/bar chart), Personal Fit Score, explanation bullets, alternative suggestions (local cache lookup). Action buttons: 'Re-analyze', 'Save to Favorites', 'Not Interested' feedback. | 5 | 20 | Frontend Dev | P1.7, P1.8, P1.9 | Pending
P1.11 | Feedback Loop Engine | User feedback ('Not Interested', 'Saved', 'Purchased') updates Genome via weighted gradient descent (local, no server). Implement conservative learning rate to avoid overfitting to single actions. | 6 | 16 | ML Engineer | P1.8, P1.10 | Pending
P1.12 | Product Cache & Indexing | IndexedDB cache for analyzed products (TTL 7 days). Index by ASIN for deduplication. LRU eviction when store exceeds 50MB. Background cleanup via alarms API. | 6 | 12 | Backend Dev | P1.2, P1.4 | Pending
P1.13 | Privacy & Compliance Shell | Privacy Notice component (popup + options). Data Export to JSON (one-click). Secure Data Wipe (overwrite then delete, with confirmation). Compliance info section with CWS Limited Use summary. | 7 | 16 | Frontend Dev | P1.2 | Pending
P1.14 | End-to-End Integration Testing | Playwright test suite: install → onboarding → scrape product → compute scores → display results → export data → wipe data. Test on Amazon search, product, and review pages. | 7 | 20 | QA / Tech Lead | P1.10, P1.13 | Pending
P1.15 | Bundle Optimization & Store Prep | Tree-shaking audit (webpack-bundle-analyzer equivalent). Minify and verify bundle < 2.5MB. Prepare store assets: screenshots, description, privacy policy URL. Submit to Chrome Web Store (dev channel). | 8 | 20 | Tech Lead | P1.14 | Pending
Phase 1 Summary
Total Tasks | 15 | Total Effort (hrs) | 276 | Duration (weeks) | 8
WEEK ALLOCATION LEGEND
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8

## Phase 2 - Extended MVP
Phase 2 — Extended MVP (Weeks 9-14)
Goal: Ethical Bundle Optimizer, product analysis caching, Amazon Creators API (Deep Check), and full Options Page
ID | Task Name | Description / Deliverables | Week | Effort (hrs) | Owner | Dependencies | Status
P2.1 | Options Page Architecture | Full-page React app (WXT options entrypoint). Navigation: Settings, Privacy, Genome Editor, Deep Check, About. Responsive layout with shadcn/ui Tabs and Cards. | 9 | 16 | Frontend Dev | P1.9 | Pending
P2.2 | Genome Editor UI | Visual editor for preference vector dimensions: sliders, toggles, category weight adjustments. Real-time preview of how changes affect past scores. Reset to defaults. Export/Import Genome JSON. | 9 | 16 | Frontend Dev | P2.1 | Pending
P2.3 | Analysis Cache Manager | IndexedDB cache with 7-day TTL and 50MB cap. Cache hit/miss analytics in Options. Manual cache flush. Smart pre-fetching for related products from search results page. | 10 | 14 | Backend Dev | P1.12 | Pending
P2.4 | Ethical Bundle Optimizer | Local-only complementary product suggestions using co-occurrence matrix (trained on public category association data, not user behavior). Bundle Score = value_sum * fit_avg * overlap_penalty. Show rationale per item. | 10 | 24 | ML Engineer | P1.7, P1.8 | Pending
P2.5 | Bundle UI Panel | Inline panel in Scout Result: 'Frequently Bought Together (Ethical)' with toggle to expand. Each bundle item shows individual True Value + Fit scores. One-click add-to-favorites for bundle items. | 11 | 16 | Frontend Dev | P2.4 | Pending
P2.6 | Amazon Creators API - OAuth | OAuth 2.0 flow for Amazon Product Advertising API (PA-API 5.0). Scope limited to item lookup only. Deep Check opt-in gate: explicit user consent before any external API call. Token refresh logic. | 11 | 20 | Backend Dev | P2.1 | Pending
P2.7 | Deep Check Integration | When user triggers Deep Check: call PA-API for real-time price, availability, and additional attributes. Merge with local analysis. Cache API response (TTL 1 hour). Rate limit: max 10 calls/minute. | 12 | 20 | Backend Dev | P2.6 | Pending
P2.8 | Advanced Privacy Controls | Granular toggles: disable caching, disable ML offscreen doc, disable Deep Check. Data audit log: view every stored record with timestamp. Scheduled auto-wipe (optional, configurable interval). | 12 | 14 | Frontend Dev | P2.1 | Pending
P2.9 | Cross-Page Genome Sync | Synchronize Genome updates across all extension contexts (popup, options, content script) via chrome.storage.onChanged listeners. Prevent race conditions with versioning/timestamps. | 13 | 12 | Backend Dev | P2.2 | Pending
P2.10 | Performance & Regression Testing | Lighthouse audit in extension popup. ML inference benchmark: measure WebNN vs WASM vs CPU latency. Memory profiling for offscreen document. Stress test: 100 consecutive analyses without crash. | 13 | 16 | QA / Tech Lead | P2.5, P2.7 | Pending
P2.11 | Store Release & Monitoring | Production build, source maps stripped. Chrome Web Store release (prod). Error tracking (local-only log export, no telemetry). Review response plan for policy questions. | 14 | 16 | Tech Lead | P2.10 | Pending
Phase 2 Summary
Total Tasks | 11 | Total Effort (hrs) | 184 | Duration (weeks) | 14
PROJECT TOTALS (Phase 1 + Phase 2)
Combined Tasks | 28 | Combined Effort (hrs) | 460 | Total Duration (weeks) | 22

## Tech Stack & Architecture
Tech Stack & Architecture Decisions
FRAMEWORK COMPARISON (WXT vs Plasmo vs CRXJS)
Criteria | WXT | Plasmo | CRXJS | Research Evidence
Maintenance Status | Active (2025) | Stagnant / maintenance mode | Revived but unstable history | WXT: regular releases; Plasmo: PRs/issues unhandled for months [1][2]
Underlying Bundler | Vite | Parcel | Vite | Vite has superior tree-shaking and HMR; Parcel has upstream bugs unpatched [2][3]
Build Size (example) | ~400 KB | ~700 KB | Varies | Migration case study: same extension 700KB → 400KB [3]
HMR Reliability | Excellent | Poor / React-only | Excellent | WXT HMR works across all contexts; Plasmo often requires full reload [2]
Framework Lock-in | Low (Vite standard) | High (Parcel abstraction) | Low | If WXT dies, migrating to Vite directly is trivial [3]
Auto-imports | Yes | No | No | WXT auto-imports boost productivity; not available elsewhere [1]
Cross-browser | Chrome, Edge, Firefox | Chrome, Edge, Firefox | Chrome only (MV3) | WXT and Plasmo support all major browsers [1]
Manifest V3 Support | First-class | First-class | Partial | CRXJS cannot build MV2+MV3 from same codebase [1]
RUNTIME ARCHITECTURE (MV3 Isolated Contexts)
Layer | Technology | Responsibilities | Constraints
Background (Service Worker) | TypeScript / WXT | Event routing, storage orchestration, offscreen lifecycle, message hub | No DOM access; terminates when idle; persist state in chrome.storage only
Content Script | TypeScript + Shadow DOM UI | Page scraping (JSON-LD + DOM fallback), inject Scout Result panel, send data to background | Isolated world; no access to page JS variables; CSP restrictions
Popup | React 19 + shadcn/ui | Quick Scout trigger, Genome summary, recent analyses, onboarding entry | Closes on blur; must be lightweight; no persistent state
Options Page | React 19 + shadcn/ui | Genome editor, privacy controls, export/wipe, Deep Check toggle, compliance info | Full-page SPA; can use localStorage (but prefer chrome.storage)
Offscreen Document | ONNX Runtime Web / WebNN | Heavy ML inference: embedding extraction, score computation, optional LLM deobfuscation | No chrome.storage/tabs APIs; only chrome.runtime messaging; invisible DOM
DATA FLOW & MESSAGE PASSING
Step | From | To | Message Type | Payload
1 | User | Popup | CLICK | Trigger Scout on active tab
2 | Popup | Background | SCRAPE_REQUEST | { tabId, action: 'analyzeProduct' }
3 | Background | Content Script | EXECUTE_SCRAPER | Inject scraper function via scripting.executeScript
4 | Content Script | Background | PRODUCT_DATA | { asin, title, price, rating, reviewCount, jsonLd, url }
5 | Background | Offscreen | COMPUTE_SCORES | { productData, genomeVector }
6 | Offscreen | Background | SCORE_RESULT | { trueValue: 78, personalFit: 82, breakdown: {...} }
7 | Background | Content Script | RENDER_PANEL | Score data + alternative suggestions
8 | User | Content Script | FEEDBACK | { action: 'notInterested' ¦ 'saved' ¦ 'purchased', asin }
9 | Content Script | Background | UPDATE_GENOME | Feedback vector for gradient update
10 | Background | Popup | SYNC_STATE | Updated Genome + recent analyses list
SECURITY & ENCRYPTION MODEL
Component | Mechanism | Standard | Rationale
Key Derivation | PBKDF2 (SHA-256, 600K iterations) | NIST SP 800-132 | Slows brute-force attacks; 600K is OWASP 2023 recommendation [5]
Symmetric Encryption | AES-GCM-256 | NIST FIPS 197 | Authenticated encryption prevents tampering; 256-bit key length [6]
Random IV Generation | crypto.getRandomValues(12 bytes) | Web Crypto API | 96-bit nonce is standard for AES-GCM; never reuse IV with same key [6]
Key Storage | Derived key held in memory only; not persisted | Zero-trust local model | If key is stored on disk, infostealers can decrypt; memory-only is password-manager pattern [5]
Data Storage | chrome.storage.local + IndexedDB | Chrome Extension APIs | chrome.storage is sandboxed per-extension; IndexedDB for structured large objects [7]
CSP | script-src 'self' 'wasm-unsafe-eval' | Manifest V3 CSP | Required for ONNX Runtime WASM backend; no inline scripts allowed [8]

## Compliance Matrix
Compliance Matrix
Chrome Web Store policies, Amazon/FTC regulations, and privacy-law alignment
CHROME WEB STORE DEVELOPER PROGRAM POLICIES
Policy Requirement | Implementation | Verification Method | Priority | Owner
Limited Use: collect only data required for single purpose | Genome stored locally only; no remote transmission; scraped product data discarded after scoring unless user saves | Code audit + network proxy test (confirm zero external calls) | Critical | Tech Lead
No sale/transfer of user data to third parties | No analytics SDKs, no tracking pixels, no data brokers. Amazon API only used after explicit opt-in. | Dependency audit (package.json review); network test | Critical | Tech Lead
Prominent Disclosure for non-obvious data collection | Privacy Notice shown in onboarding and Options. 'What we collect' summary in popup footer. | UX review: disclosure visible within 1 click from any screen | High | Frontend Dev
Encrypt sensitive user data | AES-GCM-256 for Genome and saved products. HTTPS for any external API (Deep Check only). | Penetration test: extract storage files, verify ciphertext | High | Backend Dev
Minimum functionality / no broken features | All UI buttons wired to real functions. No placeholder screens. Graceful error handling for scraping failures. | Manual QA + automated Playwright test suite | High | QA
No misleading or unexpected behavior | Extension performs exactly as described: on-demand analysis only. No hidden auto-scraping. | Code review + dynamic analysis (monitor background activity) | High | Tech Lead
Accurate metadata and privacy labels | CWS listing includes: privacy policy URL, data usage cert, single purpose description, screenshot accuracy. | Pre-submission checklist against CWS guidelines | Medium | Tech Lead
Affiliate Disclosure (if applicable) | Extension does NOT generate affiliate links. If future monetization added, explicit '#ad' or 'Paid link' disclosure required. | Legal review of any monetization feature | Medium | Product Owner
AMAZON & FTC COMPLIANCE
Rule | Requirement | Implementation | Risk if Violated | Owner
No affiliate link injection | Extension must never modify Amazon URLs to add affiliate tags | Scraper extracts data only; all links remain unmodified Amazon URLs | Amazon Associates termination; FTC fine up to $51,744/violation | Tech Lead
No auto-navigation | User must explicitly trigger every action | All analysis requires explicit click. No page redirects, no auto-add-to-cart. | CWS removal; user trust erosion | Frontend Dev
No bulk scraping / data harvesting | PA-API is for displaying products to end users, not internal bulk analytics | Deep Check limited to single product lookup per user action; rate limiting enforced | API key revocation; legal action | Backend Dev
Accurate pricing (if displayed) | Prices must come from Amazon API, not cached or manual | Deep Check fetches live price. Local analysis does NOT display price (only score). | Amazon TOS violation | Backend Dev
FTC Endorsement Disclosure | Material connection must be disclosed clearly and conspicuously | No endorsements in MVP. Future monetization requires '#ad' or 'Paid link' near any compensated recommendation. | FTC civil penalty; CWS removal | Product Owner
Data Minimization (GDPR/CCPA) | Collect only necessary data; provide deletion mechanism | Genome is 8-12 dimensions max. One-click secure wipe deletes all local data. Export provided. | Regulatory fine; class action risk | Tech Lead
PRIVACY CONTROLS IMPLEMENTATION CHECKLIST
Control | Location | Status | User Action Required
View all stored data | Options Page > Privacy | Required | User clicks 'View Data' → JSON preview
Export data to JSON | Options Page > Privacy | Required | User clicks 'Export' → download genome.json
Secure data wipe | Options Page > Privacy | Required | User clicks 'Wipe All Data' → confirmation dialog → overwrite + delete
Disable Deep Check / external API | Options Page > Deep Check | Required | User toggles off → all external calls blocked
Disable product caching | Options Page > Privacy | Recommended | User toggles off → no product data retained beyond session
Disable ML offscreen document | Options Page > Advanced | Optional | User toggles off → scores computed with lightweight heuristics only
Onboarding consent | First-run wizard | Required | User must click 'I understand' on privacy summary before proceeding
Privacy policy link | Popup footer + CWS listing | Required | User can open linked privacy policy any time

## Risk Register
Risk Register
Technical, legal, and market risks with probability/impact scoring and mitigation strategies
ID | Risk Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Owner
R1 | Technical | Amazon DOM structure changes break scraper extraction | Medium | High | 2 | Dual-strategy: JSON-LD primary (stable schema.org) + DOM fallback with conservative selectors. Weekly automated test on top-100 ASINs. | QA
R2 | Technical | Bundle size exceeds 2.5MB due to ML model weight or dependencies | Medium | Medium | 2 | Use quantized ONNX models (int8). Dynamic import for ML modules. Tree-shake shadcn/ui to used components only. Monitor with vite-bundle-analyzer. | Tech Lead
R3 | Technical | WebNN / ONNX Runtime Web incompatible with user's Chrome version | Low | High | 1 | Graceful degradation: detect WebNN support → fallback to WASM → fallback to pure-JS heuristics. Minimum Chrome version 116 (WebNN stable). | ML Engineer
R4 | Technical | Service worker terminates during long ML inference, corrupting state | Low | High | 1 | All heavy computation runs in offscreen document (persistent). Background worker only orchestrates; no inference in service worker. | Backend Dev
R5 | Legal | Chrome Web Store rejects submission due to perceived data collection risk | Medium | High | 2 | Pre-submission policy audit. Include privacy policy URL, Limited Use certification, and single-purpose explanation. Prepare reviewer notes addressing common rejection reasons. | Product Owner
R6 | Legal | Amazon interprets scraping as TOS violation and blocks extension users | Low | High | 1 | Scraper reads publicly visible DOM/JSON-LD only (no API abuse). No bulk downloading. Rate-limit internal requests. Include TOS compliance statement in privacy policy. | Tech Lead
R7 | Legal | FTC or Amazon affiliate enforcement action due to future monetization | Low | High | 1 | MVP has zero affiliate links. Future monetization requires independent legal review and conspicuous '#ad' disclosure before any paid recommendation feature ships. | Product Owner
R8 | Market | User distrust due to AI-powered extension privacy scandals (e.g. Incogni 2025 report) | Medium | Medium | 2 | Differentiate via transparency: open-source Genome logic, local-only processing badge, third-party privacy audit. No permissions beyond minimum (activeTab, scripting, storage). | Product Owner
R9 | Market | Competitor releases similar feature natively in Amazon app/website | Medium | Medium | 2 | Focus on differentiation: ethical bundle optimizer, repairability scores, local privacy. Build community around transparency values that Amazon cannot replicate. | Product Owner
R10 | Technical | React 19 concurrent features cause compatibility issues in extension contexts | Low | Medium | 1 | Test React 19 in all contexts (popup, options, shadow DOM). Use stable createRoot API. Avoid experimental APIs. Maintain fallback to React 18 if critical issues arise. | Frontend Dev
R11 | Technical | PBKDF2 key derivation too slow on low-end devices (budget Chromebooks) | Low | Medium | 1 | Benchmark on low-end hardware. If > 2s, reduce iterations to 100K with compensating UI (progress indicator). Cache derived key in memory for session duration. | Backend Dev
R12 | Technical | Genome feedback loop overfits to recent behavior, degrading recommendations | Medium | Medium | 2 | Conservative learning rate (α ≤ 0.05). Cap maximum single-update magnitude. Implement 'recency bias' correction by weighting time-decay into feedback. | ML Engineer
RISK SUMMARY
High Risks (Score ≥ 6) | 0 | Medium Risks (Score 4-5) | 0 | Low Risks (Score ≤ 3) | 12

## Sources & References
Sources & References
Academic papers, official documentation, and technical references cited across the implementation plan
Ref | Source Title | Type | URL / Citation | Relevance to Plan
[1] | WXT Official Documentation & Comparison | Official Docs | https://wxt.dev/guide/resources/compare | Framework selection; WXT vs Plasmo vs CRXJS feature matrix
[2] | Redreamality: 2025 State of Browser Extension Frameworks | Technical Analysis | https://redreamality.com/blog/the-2025-state-of-browser-extension-frameworks/ | WXT leadership rationale; maintenance status; bundler comparison
[3] | JetWriter: Why We Migrated from Plasmo to WXT | Case Study | https://jetwriter.ai/blog/migrate-plasmo-to-wxt | Real-world migration data: bundle size 700KB→400KB; HMR reliability
[4] | Dev.to: React 19 in Browser Extensions (2026) | Technical Guide | https://dev.to/johalputt/deep-dive-how-react-19-works-in-browser-extensions | React 19 concurrent mode reduces content script latency 68ms; Offscreen API
[5] | Medium: Securely Encrypting Data in Chrome Extension | Security Guide | https://codeguyakash.medium.com/securely-encrypting-data-in-a-chrome-extension | AES-GCM + PBKDF2 pattern for extension local storage; key management strategies
[6] | W3C Web Cryptography API Level 2 | Standard | https://w3c.github.io/webcrypto/ | SubtleCrypto specification; AES-GCM-256 and PBKDF2 algorithm definitions
[7] | Medium: Transformers.js + ONNX Runtime WebGPU in Chrome Extension | Technical Guide | https://medium.com/@GenerationAI/transformers-js-onnx-runtime-webgpu-in-chrome-extension | Offscreen document architecture for WASM/WebGPU ML in MV3; manifest configuration
[8] | ONNX Runtime: WebNN Execution Provider | Official Docs | https://onnxruntime.ai/docs/tutorials/web/ep-webnn.html | WebNN EP usage; device selection; performance characteristics
[9] | Shift8web: Chrome Extension for Amazon Fake Review Audit | Case Study | https://shift8web.ca/building-a-chrome-extension-to-fight-amazons-fake-review-problem/ | URL-first ASIN detection; JSON-LD vs DOM scraping; AJAX pagination handling
[10] | Gori & Pucci: ItemRank (IJCAI 2007) | Academic Paper | https://www.ijcai.org/Proceedings/07/Papers/444.pdf | Random-walk scoring algorithm for recommender engines; theoretical basis for True Value Score
[11] | arXiv: On-Device Recommender Systems Survey (2024) | Academic Survey | https://arxiv.org/html/2401.11441v3 | DeviceRS taxonomy; federated/decentralized recommendation; privacy risks and countermeasures
[12] | ScienceDirect: Multi-Armed Bandits in Recommendation Systems (2022) | Academic Paper | https://www.sciencedirect.com/science/article/abs/pii/S0957417422001543 | MAB framework for exploration-exploitation balance; systematic literature review
[13] | Brave: Federated Learning for On-Device Recommendations | Research Blog | https://brave.com/blog/federated-learning/ | Privacy-preserving local recommendation using differential privacy; HR@10 benchmarks
[14] | Chrome Web Store Developer Program Policies | Policy | https://developer.chrome.com/docs/webstore/program-policies/policies | Limited Use requirements; data handling rules; permission minimization; affiliate disclosure
[15] | Geniuslink: Amazon Affiliate Disclosure Guide | Compliance Guide | https://geniuslink.com/blog/amazon-affiliate-disclosure-guide/ | FTC and Amazon disclosure requirements; civil penalty amounts; disclosure placement rules
[16] | arXiv: Preserving Privacy in LLM-Based Product Recommendations (2025) | Academic Paper | https://arxiv.org/html/2505.00951v1 | Hybrid local/server recommendation with obfuscation; on-device Llama 3.2 inference benchmarks
[17] | Schema.org Product Specification | Standard | https://schema.org/Product | JSON-LD structured data format for product extraction; name, offers, aggregateRating fields
[18] | MadDevs: Running AI Models Locally in Browser | Technical Guide | https://maddevs.io/writeups/running-ai-models-locally-in-the-browser/ | Transformers.js WebGPU inference latency (~20ms GPU, ~120ms CPU); quantization strategy
[19] | Journal of Parallel and Distributed Computing: FedNeuMF (2024) | Academic Paper | https://www.sciencedirect.com/science/article/abs/pii/S0743731522002477 | Federated collaborative filtering with microservices; privacy-preserving distributed recommendation
[20] | Developerway: Bundle Size Investigation Guide | Technical Guide | https://www.developerway.com/posts/bundle-size-investigation | Tree-shaking patterns; namespace import anti-patterns; bundle analysis methodology